## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding complete project requirements and end-to-end workflow | Conducted mentor explanation session + reviewed documentation
Sprint 1 | Day 5 | Confusion in Python fundamentals while practicing | Revisited topics and practiced additional programs
Sprint 2 | Day 8 | Challenge in correctly mapping Google Sheets with the project | Re-checked credentials & used proper API token mapping with mentor assistance
Sprint 2 | Day 10 | Difficulty understanding OOPS + Module imports for project structure | Watched tutorials + mentor support + hands-on practice
Sprint 2 | Day 13 | Environment setup issues (Virtual environment + installation errors) | Re-installed dependencies & verified installation using mentor guidance
Sprint 3 | Day 16 | Twitter / social media API integration issues (Auth failure) | Updated keys & corrected API endpoint calls
Sprint 3 | Day 18 | Groq API credential errors | Requested new API key and corrected environment variables
Sprint 3 | Day 20 | Difficulty generating multiple content variations automatically | Implemented fallback mechanism + prompt improvements
Sprint 4 | Day 24 | Sentiment analysis results inconsistent → classification confusion | Validated results using additional datasets & mentor guidance
Sprint 4 | Day 26 | Slack message push not working initially | Updated correct webhook and verified connection
Sprint 4 | Day 28 | Streamlit deployment blank page | Debugged layout errors & re-ran server + fixed imports
Sprint 4 | Day 29 | A/B Testing “recommended” key error → app crash | Fixed code logic + added default return values
Sprint 4 | Day 30 | Google Sheets logs not visible due to connectivity timeout | Added retry handling + verified internet permissions

## Sprint Backlog
L
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Foundations and Prerequistes for doing the project | 23rd sep | 7th oct | Eligeti Nikhitha | Foundation basics of python for project | Done |  | Introduction | Python and jupyter installation done | Learnt Naming conventions | Important datatypes and the uses are learnt | Practiced basic programs for better understanding | Practiced basic fundamentals | Learned Flow Controls in python | Learned Strings in python | Worked on flow controls examples | Practiced Strings in python like creating,accessing,etc... | Learnt string methods and python function | Practiced functions | implementation of strings,function and slicing | Indetail explanation of functions
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th oct | 22nd Oct | Eligeti Nikhitha | Understanding project and architecture structure setup,Integration of googlesheet | Done |  | Understanding OOPS concept | Learnt how to use packages | Introduction to NLP and text wrangling process | Understood NLTK library and spaCy library concepts | Revised and practiced use of spaCy library | Introduction and basics about the Project | Explained about project | Understood how to Install Virtual Environment | Learned about Hugging Face Transformers | Project understanding interactive session | Practiced Hugging Face transformers | Revised the concepts and LLMs | Revised NLP and python libraries | Google Sheet Intergration is done
3 |  | Social Media Integration, Content Creation, Optimization | 23rd oct | 6th Nov | Eligeti Nikhitha | Studied social media api integraion and content generation techniques with practical exp. | Done |  | API Integration with twitter | Hands-on Twitter API Integration | Understanding LinkedIn and Instagram integration | Working on LinkedIn API Integration | Understanding progress and Interactive session | Revision and practicing API Integration | Generation of Mock data and Content Categorisation | Content Created using LLM and groq API | Understanding of gsheet_connector | Understood Gen AI and LLM Fundamentals | Revision of LLM | Interactive Session | Understood about Generation of versions of content | Hands on generation of different versions of content
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | Eligeti Nikhitha | Learned Sentiment Analysis, Slack Integration and deployment on streamlit | Done |  | Understood about API and stages of it | Clearly understood about API | Revised and practiced API concepts | Worked on Assignment | Interactive and engagement session | Understand about content optimization | Learned about Sentiment Analysis | Understand about slack integration | Learned about A/B Testing | Revisied the concept of A/B testing | Revised and Practiced Sentiment Analysis | Understood about Project Workflow | Presentation preparation and discussion | Mock presentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-25 | 2025-10-07 | Eligeti Nikhitha | Practicing Python fundamentals with coding tasks | Just reading theory without hands-on | Revision after each concept | Completed Python basics (variables, strings, loops, functions) and built small practice programs
2 | Sprint 2 | 2025-10-08 | 2025-10-22 | Eligeti Nikhitha | Setting up APIs and the project environment properly | Delaying environment setup and integrations | Clarifying doubts with mentor | Integrated Google Sheets with API credentials and set up the project structure successfully
3 | Sprint 3 | 2025-10-23 | 2025-11-06 | Eligeti Nikhitha | Working on social media integration and content generation | Trying to test everything manually first | Improving content generation features with Groq/Gemini | Successfully implemented Twitter API posting, created content variations, and tested automation for posting
4 | Sprint 4 | 2025-11-07 | 2025-11-24 | Eligeti Nikhitha | Performing Sentiment Analysis, A/B Testing, and Slack notifications | Ignoring minor backend errors during testing | Improve UI and execution flow with Streamlit | Integrated sentiment engine, A/B test comparison, Slack alerts & executed full pipeline end-to-end